## Slide 1: Example Release Schedule
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Fishy Fish
Release x Kick-Off
New Features Developed
Stabilize
Patch Updates
App Development
Release (x+1) Kick-Off
RC1
RC2
RC3
Final Release (x)
x.0.1
x.0.2
x.0.3
x.0.4

## Slide 2: Release Candidates
RC1
RC3
RC2
Core Feature Freeze
Platform Freeze
Core APIs Frozen (App FW, Public Services, GUI Toolkit)
SDK available for App Developers on at least 1 Reference Board
Final RC
Reference Applications Frozen
Documentation Complete
SDK for All Reference Boards
Final
Release
BSPs Frozen
Release Branch Created
All source code frozen (SRCREV pinned) (all RCs now)
Test Cases Frozen

## Slide 3: 2017 AGL Schedule
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Charming Chinook
3.0.0
3.0.2
3.0.1
3.0.3
3.0.4
Daring Dab
Feature Development
Electric Eel
RC1
RC3
RC4
RC2
Feature Development
As of 31 Dec 2017
RC1
RC3
4.0.0
4.0.3
4.0.1
4.0.2
4.0.4
RC2
3.0.5
RC5
Final

## Slide 4: 2018 AGL Schedule
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Electric Eel
5.0.0
5.0.2
5.0.1
5.0.3
5.1.0
Funky Flounder
Feature Development
Grumpy Guppy
RC1
RC3
RC2
Feature Development
As of 31 Dec 2018
RC1
RC3
RC4
6.0.0
6.0.1
6.0.3
RC2
5.1.1
6.0.2
Final

## Slide 5: 2019 AGL Schedule
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Grumpy Guppy
RC4
7.0.2
7.0.0
7.0.3
7.0.1
Happy Halibut
Itchy Icefish
Start of
Development
As of 24 May 2019
8.0.0
8.0.1
8.0.3
Release Candidates
7.0.4
8.0.2
Release Candidates
RC5
Start of Development
8.0.4

## Slide 6: 2019 AGL Schedule
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Grumpy Guppy
RC4
7.0.2
7.0.0
7.0.3
7.0.1
Happy Halibut
Itchy Icefish
Start of
Development
As of 24 May 2019
8.0.0
8.0.1
8.0.3
Release Candidates
7.0.4
8.0.2
Release Candidates
RC5
Start of Development
8.0.4
AMM
F2F
F2F
F2F
AMM
ALS
F2F

## Slide 7: Daring Dab
May | Jun | Jul | Aug | Sep | Oct
Daring Dab
New Features
Stabilize
Patch Updates
App Development
RC1
5.31
RC2
7.05
Final Release 7.28
RC3
7.21
4.0.1
4.0.2
Final

## Slide 8: Daring Dab Patch Releases
Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Daring Dab
Stabilize
Patch Updates
App Development
Final Release 7.28
4.0.1
9.18
4.0.2
10.15
4.0.3
2.14
As of 14 Feb 2018
Final

## Slide 9: Electric Eel
Jul | Aug | Sep | Oct | Nov | Dec | Jan
Electric Eel
New Features Developed
Stabilize
Patch Updates
App Development
RC2
11.05
RC4
12.10
RC3
11.30
5.0.0
1.10
0
Start of Development
7.10
RC1
10.22
As of 22 Jan 2018
RC5
12.22
Final

## Slide 10: Electric Eel Patch Releases
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
Electric Eel
Patch Updates
App Development
5.0.0 Release 01.10
5.0.1
2.14
5.0.2
4.4
5.0.3
5.29
5.1.0
07.30
As of 12 October 2018
Final

## Slide 11: Funky Flounder
Apr | May | Jun | Jul | Aug | Sep
Funky Flounder
New Features Developed
Stabilize
App Development
RC1
7.6
RC2
07.27
Final Release 10.8
RC3
8.17
Start of Development
1.15
As of 12 October 2018
RC4
8.24
RC5
9.5
RC6
9.13
RC7
9.17
Final

## Slide 12: Funky Flounder Patch Releases
Oct | Nov | Dec | Jan | Feb | Mar
Funky Flounder
Patch Updates
App Development
6.0.0 Release 10.8
6.0.1
10.29
6.0.2
11.15
6.0.3
12.12
6.0.4
02.04.19
As of 24 May 2019
6.0.5
03.25

## Slide 13: Grumpy Guppy
Aug | Sep | Oct | Nov | Dec | Jan | Feb
Grumpy Guppy
New Features Developed
Stabilize
App Development
RC1
11.22
RC2
12.6
Final Release 2.18.2019
RC3
12.20
Start of Development
8.01.2018
As of 20 February 2019
RC4
01.17
Final

## Slide 14: Grumpy Guppy Patch Releases
Feb | Mar | Apr | May | Jun | Jul | Aug
Grumpy Guppy
Patch Updates
App Development
7.0.0 Release 02.18
7.0.1
04.18
7.0.2
05.24
7.0.3
06.30
7.0.4
07.31
As of 24 May 2019

## Slide 15: Happy Halibut
Feb | Mar | Apr | May | Jun | July
Happy Halibut
New Features Developed
Stabilize
App Development
RC1
05.10
RC2
05.24
Final Release 7.06
RC3
06.08
Start of Development
02.07
As of 24 May 2019
RC4
06.23
Uprev to thud complete
03.22

## Slide 16: Happy Halibut Patch Releases
Jul | Aug | Sep | Oct | Nov | Dec | Jan
Happy Halibut
Patch Updates
App Development
8.0.0 Release 07.13
8.0.1
09.07
8.0.2
10.12
8.0.3
11.15
8.0.4
12.14
As of 24 May 2019
8.0.5
01.25

## Slide 17: Itchy Icefish
Aug | Sep | Oct | Nov | Dec | Jan
Itchy Icefish
New Features Developed
Stabilize
App Development
RC1
11.22
RC2
12.6
Final Release 02.07.20
RC3
12.20
Start of Development
07.01
As of 24 May 2019
RC4
01.25